## Feuil1
Task name | OBS | Duration | Role
Create professionnal network
Do the Development Phase
Run a presentation meeting with university | PM / Assistant | 1h | 2
- Ask for subventions
- Ask for contact details
- Ask for a place
- Ask for contact details about informatics students
Contact alumni | Secretary | 2weeks | M
Find a student to build up the website | Recruiter |  | A
- Recrutement
Obtain subventions | Financial |  | M
Build up the website | Informatician | 1week | S
Propose to alumni to complete their profile | Secretary |  | A
Ask alumni for a date | Secretary |  | A
Fix a date for the meeting | Secretary |  | A
Write a first newsletter | Journalist |  | M
Organize the evening | Organizer |  | 2
Do the Qualify Phase
Check that internships/jobs have been proposed | Pollster |  | M
Ask by mail if the meeting went well | Pollster |  | M
Do the Lifecycle Phase
Find successors for the project | Recruiter |  | A
Write a newsletter | Journalist |  | A/M